## Sheet1
Prodrive Motowerks System
Done
On-Going
Plan
|  |  | Late | [6 empty] | 1st Week | [6 empty] | 2nd Week | [6 empty] | 3rd Week | [6 empty] | 4th Week | [6 empty] | 5th Week
[10 empty] | Mon | Tue | Wed | Thu | Fri | Sat |  | Mon | Tue | Wed | Thu | Fri | Sat |  | Mon | Tue | Wed | Thu | Fri | Sat |  | Mon | Tue | Wed | Thu | Fri | Sat
WBS | Task | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2013-04-08 | 2013-04-09 | 2013-04-10 | 2013-04-11 | 2013-04-12 | 2013-04-13 | 2013-04-14 | 2013-04-15 | 2013-04-16 | 2013-04-17 | 2013-04-18 | 2013-04-19 | 2013-04-20 | 2013-04-21 | 2013-04-22 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-26 | 2013-04-27 | 2013-04-28 | 2013-04-29 | 2013-04-30 | 2013-05-01 | 2013-05-02 | 2013-05-03 | 2013-05-04 | 2013-05-05 | 2013-05-06 | 2013-05-07 | 2013-05-08 | 2013-05-09 | 2013-05-10 | 2013-05-11
1 | System Design | Kenn | 2013-04-08 | 2013-04-25 | bar: 2013-04-08 to 2013-04-13; 2013-04-15 to 2013-04-20; 2013-04-22 to 2013-04-25
1.1 | Database Schema | Kenn | 2013-04-08 | 2013-04-25 | bar: 2013-04-08 to 2013-04-13; 2013-04-15 to 2013-04-20; 2013-04-22 to 2013-04-25
2 | System Design | Kenn/Jun2x | 2013-04-08 | 2013-04-25 | bar: 2013-04-08 to 2013-04-13; 2013-04-15 to 2013-04-20; 2013-04-22 to 2013-04-25
2.1 | System Development | Kenn/Jun2x | 2013-04-08 | 2013-05-04 | bar: 2013-04-08 to 2013-04-13; 2013-04-15 to 2013-04-20; 2013-04-22 to 2013-04-27; 2013-04-29 to 2013-05-04
2.1.1 | Alamid Framework Utilities
2.1.1.1 | XML Parser | Jun2x | 2013-04-18 | 2013-04-22 | bar: 2013-04-18 to 2013-04-20; 2013-04-22 to 2013-04-24
2.1.1.2 | Form Generator | Kenn | 2013-04-25 | 2013-04-26 | bar: 2013-04-25 to 2013-04-26
2.1.2 | Master Files Entry Form | Kenn/Jun2x | 2013-04-27 | 2013-04-29 | bar: 2013-04-27; 2013-04-29
2.1.3 | Login System | Jun2x | 2013-04-27 | 2013-04-29 | bar: 2013-04-27; 2013-04-29
2.1.3 | Backup Utility | Jun2x | 2013-04-27 | 2013-04-29 | bar: 2013-04-25
2.1.4 | Restore Utility | Jun2x | 2013-04-27 | 2013-04-29 | bar: 2013-04-25
2.1.5 | hook function checker | Kenn | 2013-04-25 | 2013-04-25 | bar: 2013-04-25
2.1.6 | alamid table name retriever | Jun2x | 2013-04-25 | 2013-04-25 | bar: 2013-04-25
3 | Meeting with the users | Kenn/Jun2x/Emz | 2013-04-23 | 2013-04-23 | bar: 2013-04-23
4 | Documentation | Emz | 2013-04-29 | 2013-05-04 | bar: 2013-04-29 to 2013-05-04
4.1 | Help System ( scout for) | Emz | 2013-04-23 | 2013-04-27 | bar: 2013-04-23
4.2 | Alamid Framework - Dev Guide | Emz | 2013-04-24 | 2013-04-27 | bar: 2013-04-24 to 2013-04-27
5 | Installation | Kenn/Jun2x | 2013-05-06 | 2013-05-06 | bar: 2013-05-06
6 | Training | Emz | 2013-05-06 | 2013-05-07 | bar: 2013-05-06 to 2013-05-07
7 | Implementation | Emz | 2013-05-08 | 2013-05-11 | bar: 2013-05-08 to 2013-05-11
8 | Fine Tuning | Kenn/Jun2x | 2013-05-09 | 2013-05-11 | bar: 2013-05-09 to 2013-05-11